Stone Harbor Borough

Sanitary Sewer, Water Main, Drainage & Beach Outfall Program Phase 3

Preliminary Construction Schedule 9/14/2015

Phase 1 - 82nd Street from North Basin Street End to Second Avenue

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Sanitary Main | 9/21/2015 | 10/2/2015 |
| Sanitary Laterals | 10/12/2015 | 10/18/2015 |
| Water Main | 10/5/2015 | 10/9/2015 |
| Water Services | 10/19/2015 | 10/25/2015 |
| Storm Sewer | 10/26/2015 | 11/23/2015 |
| Concrete Curbs and Flatwork | 11/23/2015 | 12/21/2015 |
| Roadway Subbase and HMA Base Course | 12/21/2015 | 12/31/2015 |

Phase 2 Second Ave from 82nd Street to 81st Street 81st Street from Second Avenue to First Avenue First Avenue from 81st Street to 83rd Street

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Water Main | 12/11/2015 | 12/18/2015 |
| Storm Sewer | 11/23/2015 | 12/11/2015 |
| Concrete Curbs and Flatwork | 12/21/2015 | 12/31/2015 |
| Roadway Subbase and HMA Base Course | 1/4/2016 | 1/18/2016 |

Phase 3 First Avenue from 83rd Street to 84th Street 84th Street from First Avenue to beach 83rd Street from First Avenue to beach

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Sanitary Main | 1/4/2016 | 1/11/2016 |
| Sanitary Laterals | 1/11/2016 | 1/18/2016 |
| Water Main | 12/18/2015 | 12/31/2015 |
| Water Services | 1/11/2016 | 1/18/2016 |
| Storm Sewer | 1/18/2016 | 2/5/2016 |
| Recharge Basins | 2/5/2016 | 2/26/2016 |
| Concrete Curbs and Flatwork | 2/26/2016 | 3/25/2016 |
| Roadway Subbase and HMA Base Course | 3/25/2016 | 4/8/2016 |

Phase 4 First Avenue from 84th Street to 86th Street 86th Street from First Avenue to beach 85th Street from First Avenue to beach

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Sanitary Main | 3/4/2016 | 3/11/2016 |
| Sanitary Laterals | 3/11/2016 | 3/25/2016 |
| Water Main | 2/26/2016 | 3/4/2016 |
| Water Services | 3/11/2016 | 3/25/2016 |
| Storm Sewer | 3/25/2016 | 4/22/2016 |
| Recharge Basins | 4/22/2016 | 5/6/2016 |
| Concrete Curbs and Flatwork | 4/29/2016 | 5/27/2016 |
| Roadway Subbase and HMA Base Course | 5/27/2016 | 6/10/2016 |
| Removal of Existing Beach Outfalls, 84th and 86th Streets | 5/6/2016 | 5/20/2016 |

Phase 5 First Avenue from 86th Street to 88th Street 88th Street from First Avenue to beach 87th Street from First Avenue to beach

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Sanitary Main | 9/16/2016 | 9/23/2016 |
| Sanitary Laterals | 9/23/2016 | 10/7/2016 |
| Water Main | 9/12/2016 | 9/16/2016 |
| Water Services | 9/23/2016 | 10/7/2016 |
| Storm Sewer | 10/7/2016 | 10/28/2016 |
| Recharge Basins | 10/28/2016 | 11/18/2016 |
| Concrete Curbs and Flatwork | 11/18/2026 | 12/16/2016 |
| Roadway Subbase and HMA Base Course | 12/16/2016 | 12/30/2016 |

Phase 6 First Avenue from 88th Street to 89th Street 89th Street from First Avenue to beach

|  |  |  |
| --- | --- | --- |
|  | Start | Completion |
| Sanitary Main | 11/18/2016 | 11/25/2016 |
| Sanitary Laterals | 11/25/2016 | 12/2/2016 |
| Water Main | 11/18/2016 | 11/25/2016 |
| Water Services | 11/25/2016 | 12/2/2016 |
| Storm Sewer | 12/2/2016 | 12/9/2016 |
| Recharge Basins | 12/9/2016 | 12/16/2016 |
| Concrete Curbs and Flatwork | 12/16/2016 | 12/30/2016 |
| Roadway Subbase and HMA Base Course | 1/2/2017 | 1/16/2017 |
| Removal of Existing Beach Outfalls, 88th Street | 12/9/2016 | 12/16/2016 |